SERVICE DEAL CONTRACT

Content & Marketing — Social Media Campaign

Status: PENDING ESCROW LOCK    |  Deal ID: DEAL-2026-0042

Generated by Sealed AI Agent  ·  May 9, 2026

ORIGINAL REQUEST (AS TYPED BY CLIENT)

|  | rednave2806@gmail.com via Sealed Chat · May 9, 2026, 14:32 WIB Hai, gue mau hire content creator buat bikin konten sosmed buat brand gue selama 1 bulan. Gue butuh 12 feed Instagram (campuran foto sama Reels), sama 8 postingan Twitter/X. Semua konten harus niche finance dan harus ada caption bahasa Indonesia yang engaging. Budget gue $600 USDC total, mau dibagi jadi 3 tahap: setelah draft disetujui, setelah 50% konten live, sama setelah semua selesai. Deadline keseluruhan 30 hari dari sekarang. Deal? [Translation: I want to hire a content creator for my brand's social media for 1 month. I need 12 Instagram feed posts (mix of photos and Reels) + 8 Twitter/X posts, all finance niche with engaging Indonesian captions. Budget $600 USDC split into 3 milestones: after draft approval, after 50% content is live, and after full completion. 30-day deadline.] |
| --- | --- |

1. PARTIES

| Role | CLIENT (Buyer) |
| --- | --- |
| Name / Handle | der (@rednave) |
| Email | rednave2806@gmail.com |
| Wallet Address | 8xKp...F3Qz (Phantom — Solana Devnet) |
| Role | SERVICE PROVIDER (Seller) |
| Name / Handle | TBD — awaiting provider acceptance |
| Wallet Address | TBD — auto-locked by Sealed on acceptance |

2. SCOPE OF WORK

The Provider shall deliver the following content for the Client's finance-niche brand:

- 12 Instagram feed posts — mix of static photos and Reels (min. 30s each)

- 8 Twitter / X posts — thread or standalone, finance-niche topic

- All captions written in Bahasa Indonesia — engaging, non-generic tone

- Content must be original and brand-safe (no plagiarism, no AI-slop)

- Client has final approval rights on all drafts before posting

- Revisions: up to 2 rounds per batch at no extra cost

3. PAYMENT MILESTONES & ESCROW SCHEDULE

Total contract value of $600.00 USDC is locked in Sealed escrow on deal acceptance. Funds are released automatically by the Sealed AI agent upon milestone verification.

| # | Milestone | Deliverable | Deadline | Amount (USDC) |
| --- | --- | --- | --- | --- |
| 1 | Draft Approval — all 20 content pieces approved by client | Draft files + caption doc submitted via Sealed | Day 7 | $150.00 |
| 2 | Mid-Campaign Go-Live — 50% of content (10 posts) published | Screenshot/links of 6 IG + 4 Twitter posts | Day 18 | $250.00 |
| 3 | Full Completion — all 20 posts published, analytics shared | Links to all posts + 7-day reach summary | Day 30 | $200.00 |

Dispute resolution: if either party disputes a milestone, Sealed AI agent reviews deliverable evidence on-chain and mediates. Unresolved disputes escalate to Sealed DAO arbitration.

4. TIMELINE

| Contract Start | Upon mutual wallet signature & USDC escrow lock |
| --- | --- |
| Milestone 1 Deadline | Day 7 (by May 16, 2026) |
| Milestone 2 Deadline | Day 18 (by May 27, 2026) |
| Final Deadline | Day 30 (by June 8, 2026) |
| Late Penalty | 0.5% of outstanding milestone per day, max 5% |

5. TERMS & CONDITIONS

- Intellectual property for all delivered content transfers to the Client upon full payment release.

- The Provider may not publish the content under their own brand or sell it to third parties.

- The Client agrees not to withhold milestone approval without documented, specific objections.

- Either party may cancel before Milestone 1 delivery; escrowed USDC is refunded minus a 1% Sealed protocol fee.

- This contract is governed by the Sealed smart contract on Solana. On-chain state is the final source of truth.

- Both parties agree that Sealed AI agent actions (escrow lock, release, refund) are binding and automated.

6. ON-CHAIN SIGNATURES

This contract becomes binding when both parties sign the Sealed transaction with their Solana wallets. No wet signature required — wallet signatures are legally equivalent under applicable electronic contract law.

| CLIENT der (@rednave) rednave2806@gmail.com 8xKp...F3Qz ⬛ SIGNED May 9, 2026 14:34 WIB | SERVICE PROVIDER Awaiting acceptance... Wallet: TBD ⬜ PENDING |
| --- | --- |

This contract was autonomously structured by Sealed AI Agent from a plain-language client request. All terms were inferred and confirmed by the client before escrow lock. Escrow vault: sealed-vault-DEAL-2026-0042.sol  ·  Network: Solana Devnet